## Defect Tracking Log
DEFECT TRACKING LOG
Project Name
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
5 | 07.01.2026. |  | 1.Open web browser (e.g. Google Chrome). 2.Open www.technoshop.ba web page on web browser. 3.Add a product to cart. 4.Open cart and navigate to checkout form. 5.Fill all required fields with valid data except address. 6.In Address field enter an invalid address with special characters (e.g., "@@@!!!###$$$%%%^^^&&&***((()))"). 7.Click “Checkout/Nastavite” button. 8.Checkout proceeds and validation error is not shown. EXPECTED RESULT: Checkout should be blocked and a validation error/message should be displayed. | [6 empty] | New |  |  |  |  | New
6 | 07.01.2026. |  | 1.Open web browser (e.g. Google Chrome). 2.Open www.technoshop.ba web page on web browser. 3.Add a product to cart. 4.Open cart and navigate to checkout form. 5.Fill all required fields with valid data except address. 6.In Address field enter an invalid address with only one letter (e.g., "A"). 7.Click “Checkout/Nastavite” button. 8.Checkout proceeds and validation error is not shown. EXPECTED RESULT: Checkout should be blocked and a validation error/message should be displayed. | [6 empty] | New |  |  |  |  | New
7 | 07.01.2026. |  | 1.Open web browser (e.g. Google Chrome). 2.Open www.technoshop.ba web page on web browser. 3.Ensure the search input field is empty. 4.Click the Search button/icon. 5.Search is executed and results page opens (URL changes). EXPECTED RESULT: System should ignore empty search query (or show a validation message) and stay on the same page | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
8 | 07.01.2026. |  | 1.Open web browser (e.g. Google Chrome). 2.Open www.technoshop.ba web page on web browser. 3.Input "@@@!!!###//" in the search input field. 4.Click the Search button/icon. 5.Search is executed and results page opens (URL changes). EXPECTED RESULT: System should show a validation message and stay on the same page | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
[17 empty] | Closing | Development
Testing
Documentation and Training
Deployment
Post-Deployment
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).